## Sheet1
Task | Type | Sub-task | Beginning Time | Ending Time | Note
Communication | ground | Read the state estimation data( height, velocity, acceleration, attitude, latitude, longitude, etc.) | 2021-09-08 | 2021-09-12
| ground | Send the test command to the camera and autopilot, check the responding | 2021-09-13 | 2021-09-16
| ground | Read, store, covert the RGB and IR images | 2021-09-17 | 2021-09-22
Waypoint flight | ground | Waypoint flight simulation | 2021-09-23 | 2021-09-28
| ground | Accomplish some given mission( take a photo, drop something, etc.) at a certain waypoint simulation | 2021-09-29 | 2021-10-01
| air | Fly along the given path and take the picture(RGB and IR) of the synthetic fire and smoke(an oven, if possible) | 2021-10-03 | 2021-10-04 | 1. prepare the flight test first. 2. arrange data set on the second day
Fire and smoke detection | ground | Implement the fire and smoke detector which runs on the onboard computer. | 2021-10-05 | 2021-10-10 | design the detector earlier.
| ground | Test and debug the algothrim embeded with the picture that are captured before. | 2021-10-11 | 2021-10-18
| ground | ground simulation | 2021-10-19 | 2021-10-22
| air | DJI M300 flies along the path and detects the synthetic fire and smoke along the path | 2021-10-25 | 2021-10-26 | 1. prepare the flight test first. 2. arrange data set on the second day
Detection and Navigation | air | Detect fire and Navigate around the fire according to some given strategy | ~ | ~
| air | Motion control under the navigation module after the fire is detected. | ~ | ~